AgriSmart AI

Execution Plan — Who does what, and when

SIH 2026 Internal Hackathon · L. J. Institute of Engineering and Technology · C-433

Build window: 10–15 September 2026

Team: 6 members across 6 work tracks

# Contents

1. Overview & Objective

2. Work Tracks (who owns what)

3. AI Tool Stack — setup reference

4. Sample Prompts — Claude & Antigravity/Gemini

5. Communication & File-Sharing Setup

6. Master Timeline (6-day view)

7. Day-wise Detailed Schedule (Day 1–6)

8. Daily Sync Meeting Format

9. Bonus Module Specification

10. Testing & QA Checklist

11. README & Model Report Templates

12. Glossary — Key Terms

13. Risk & Contingency Plan

14. Final Pre-Submission Checklist

15. Evaluation Criteria & Scoring Strategy

Appendix A — Shared Class List (example)

Appendix B — Credentials & Access Tracker

Appendix C — Team Working Agreement

Appendix D — Backup Plan if a Member is Unavailable

# 1. Overview & Objective

Ye document is liye hai ki Day 1 se hi kaam start ho sake — kisi ko confusion na ho ki abhi kya karna hai. Core task ek hi hai: leaf image se disease classify karna aur macro-F1 + confusion matrix report karna, held-out field-images pe. Ye compulsory hai. Baaki — weather intelligence, smart irrigation, sustainability score, GenAI farmer assistant — bonus hai; is plan me sirf 3 bonus module recommend kiye gaye hain jo purely software/API se bante hain (hardware ki zaroorat nahi).

Poora build AI-assisted hai: Claude (Sonnet) planning, spec-writing, prompt-crafting aur final code-review ke liye; Antigravity + Gemini actual code (backend, frontend, scripts) generate karne ke liye. Training Colab/Kaggle GPU pe hoga, transfer-learning backbone ke saath.

Ye document Day-1 se hi print/share karke sab track-owners ko de dena — usi din se kaam start ho sakta hai.

# 2. Work Tracks

Har track ek functional area hai. Har track ko doosre track ke saath sync me rehna hai — koi bhi track alag-thalag kaam nahi karega.

| Track | Area | Scope |
| --- | --- | --- |
| Track A | Core CV Model | Dataset preprocessing, transfer-learning training, evaluation (macro-F1, confusion matrix). Ye sabse critical track hai — isi pe core-task judge hota hai. |
| Track B | Backend & Predict Interface | Flask/FastAPI app, predict() route, model loading, error handling, unified API structure. |
| Track C | Frontend / Web UI | Upload flow, result display, loading/error states, mobile-responsive farmer-friendly design. |
| Track D | Bonus — Weather & Irrigation & Sustainability | OpenWeatherMap integration, irrigation-decision logic, sustainability-score formula. |
| Track E | Bonus — GenAI Farmer Assistant | Gemini/Claude API se grounded explanation, regional-language (Hindi/Gujarati) support. |
| Track F | Docs, Testing & Deployment | README, model report, originality declaration, Postman testing, deployment, demo video. |

Track F ka kaam har din ke saath overlap karta hai (testing aur docs continuous hote hain), isliye ye track sabse flexible hai aur support-member ke saath achha fit hota hai.

## 2.1 Track Setup Checklist

Har track ke pehle 3 setup-steps aur zaroori skill — Day 1 shuru karne se pehle ye clear kar lo.

| Track | Skill needed | First 3 steps (Day 1) |
| --- | --- | --- |
| Track A | Python, basic ML (Keras/PyTorch) | Kaggle account + PlantVillage download → Colab GPU runtime enable → class-list confirm karo. |
| Track B | Python, REST API basics | Python venv/Flask/FastAPI install → GitHub repo clone → predict() signature Claude ke spec se confirm. |
| Track C | HTML/CSS/JS ya Streamlit basics | Frontend stack decide → Antigravity se skeleton generate → backend ka dummy-response se connect. |
| Track D | API integration basics | OpenWeatherMap signup → API key test → irrigation-rule Claude se draft karwao. |
| Track E | Prompt-writing basics | Gemini/Claude API key setup → sample grounded-prompt test → regional-language plan. |
| Track F | Documentation + testing mindset | GitHub repo structure banao → Postman install → README skeleton draft. |

# 3. AI Tool Stack — setup reference

| Stage | Tool | Kaam |
| --- | --- | --- |
| Planning & specs | Claude (Sonnet) | Technical spec likhna, Antigravity/Gemini ke liye prompts banana, README/model-report drafting, final code review. |
| Code generation | Antigravity + Gemini | Har script/route/UI-component ke liye — Claude ke specific prompt se chhote-chhote pieces generate karna. |
| Training compute | Google Colab / Kaggle Notebooks | Free GPU — PlantVillage pe train, held-out field-set pe evaluate. |
| Model backbone | EfficientNet-B0 / ResNet50 (transfer learning) | Pretrained weights fine-tune, kam data me bhi accha macro-F1. |
| Weather data | OpenWeatherMap API | Live/forecast data — irrigation aur weather-intelligence module ke liye. |
| GenAI assistant | Gemini API / Claude API | Grounded explanation aur regional-language support. |
| API testing | Postman | predict() aur baaki routes ka manual endpoint testing. |
| Deployment | Streamlit Cloud / Hugging Face Spaces | Free hosting, judges ke liye live demo link. |
| Video | Any screen recorder + basic editor | 3-5 min demo recording aur trimming. |

# 4. Sample Prompts — Claude & Antigravity/Gemini

In-hi tarah ke prompts use karo — pehle Claude se detailed spec/plan lo, phir wahi spec Antigravity+Gemini ko chhote, specific pieces me do. Ek baar me 'poora app bana do' mangna avoid karo — quality gir jaati hai.

### Track A — dataset & training (Claude)

"Main PlantVillage dataset (lab images) pe train karke PlantDoc-style field images pe evaluate karna chahta hoon, shared class list ke 15-20 classes ke saath. Ek train/val/test split strategy suggest karo jo held-out set pe leakage avoid kare, aur EfficientNet-B0 transfer-learning ke liye step-by-step plan do."

### Track B — backend (Antigravity + Gemini)

"Flask app banao ek /predict route ke saath jo image file leta hai, [model-path] se loaded Keras model se prediction karta hai, aur JSON me {class_label, confidence} return karta hai. Invalid file-type aur missing-file ke liye error handling bhi add karo."

### Track D — irrigation logic (Claude, phir Antigravity se code)

"Ek simple rule likho: agar next-24h rain-probability > 60% hai to 'delay irrigation' return karo; agar soil-moisture < 30% aur rain-probability < 30% hai to 'irrigate now'; warna 'monitor'. Isko ek Python function me convert karne ke liye Antigravity prompt bhi likh do."

### Track E — grounded assistant (Claude for prompt design)

"Ek prompt template banao jo sirf diye gaye disease-name aur precaution-list ke upar based ho — bahar se koi extra medical/agricultural claim na kare. Response Hindi aur English dono me structured tarike se aana chahiye."

### Track F — code review (Claude)

"Yeh poora repo [link/paste code] review karo — bugs, security issues (hardcoded API keys, etc), aur bata do ki README ke run-instructions actually is code se match karte hain ya nahi."

# 5. Communication & File-Sharing Setup

Day 1 subah hi ye 3 cheez set kar lo, taaki din me koi confusion na ho:

- Ek group chat (WhatsApp/Discord) — sirf blockers aur urgent updates ke liye, general chat alag rakho.

- GitHub repo — sab commits yahi jaayenge, har track apni branch pe kaam kare, Track F daily merge check kare.

- Ek shared doc (Google Doc/Sheet) — API keys (private tab), bug-list, aur roz ke sync-notes ke liye.

# 6. Master Timeline (6-day view)

| Day | Goal of the day |
| --- | --- |
| 10 September — Planning, Access & Repo Setup | Sabko apna track pata ho, saare accounts/API keys ready ho, repo structure ban jaye, aur core spec Claude se likha jaye. |
| 11 September — Core Build Begins | Preprocessing + baseline training shuru, backend/frontend skeleton chalu, bonus APIs ka pehla working version. |
| 12 September — Model Freeze + Real Integration | Trained model ka evaluation lock karo, backend me real predictions jodo, frontend ko live data se connect karo. |
| 13 September — Full Integration Day | Saare modules ek hi app me merge, deploy karo, aur end-to-end poora flow test karo. |
| 14 September — QA, Documentation & Demo Prep | Code review, README + model report complete, demo video ka pehla cut ready. |
| 15 September — Final Submission Day | Sab kuch final commit, video final, repo check aur submission. |

# 7. Day-wise Detailed Schedule

Har din time-block ke hisaab se tasks diye gaye hain, track ke saath. 'All' matlab poori team involved hai (sync/testing/decision).

## Day 1 — 10 September — Planning, Access & Repo Setup

Goal: Sabko apna track pata ho, saare accounts/API keys ready ho, repo structure ban jaye, aur core spec Claude se likha jaye.

| Time | Track | Task | Tool | Output / Deliverable |
| --- | --- | --- | --- | --- |
| 9:00–9:30 | All | Kickoff call — problem statement recap, bonus combo finalize (Weather + Irrigation + GenAI Assistant), track allocation. | — | Track assignment confirm |
| 9:30–11:00 | Track A | Kaggle account setup, PlantVillage dataset download, folder-structure explore, class-list note karo. | Kaggle | Dataset local/Colab me ready |
| 9:30–11:00 | Track B | GitHub repo create karo (/src,/model,/report,/README.md), Python venv setup, Flask/FastAPI install. | GitHub, Antigravity | Repo skeleton, first commit |
| 9:30–11:00 | Track C | Frontend stack decide (plain HTML/JS ya Streamlit), basic project skeleton generate karo. | Antigravity + Gemini | Empty UI shell |
| 9:30–11:00 | Track D | OpenWeatherMap account + API key le lo, sample API call test karo (curl/Postman). | OpenWeatherMap, Postman | Working API key + sample response |
| 9:30–11:00 | Track E | Gemini API aur/ya Claude API key setup, ek sample prompt bhejke response test karo. | Gemini/Claude API | API connectivity confirmed |
| 11:00–13:00 | Track F | Claude se poora technical spec likhwao — classes list, predict() signature, folder contract, API routes list. Ye spec sabko share karo. | Claude (Sonnet) | Shared spec document |
| 14:00–16:00 | Track A | PlantDoc-style field-image sample (kickoff data) dekho, PlantVillage ke shared class-list se match karke folders arrange karo. | Kaggle/GitHub | Train/val vs held-out sample clearly separated |
| 14:00–16:00 | Track B | predict(image_path) function ka exact signature aur requirements.txt draft likho (spec ke hisaab se). | Claude → Antigravity+Gemini | requirements.txt v0, function stub |
| 14:00–16:00 | Track C | Upload-image wireframe banao (kaunsa input, kaunsa output dikhega) — Claude se ek simple diagram/plan lo. | Claude | UI wireframe |
| 14:00–16:00 | Track D | Irrigation-decision rule likho: agar rain-probability high hai to 'delay irrigation', warna soil-moisture check karo. | Claude (logic draft) | Rule written in plain steps |
| 14:00–16:00 | Track E | Farmer-assistant ke liye grounding prompt template likho — sirf model output + precaution list par based explanation, regional language toggle ka plan. | Claude | Prompt template v0 |
| 16:00–17:00 | All | Evening sync — kya blocker hai, kal (Day 2) ka target confirm karo. | — | Day 2 plan locked |

## Day 2 — 11 September — Core Build Begins

Goal: Preprocessing + baseline training shuru, backend/frontend skeleton chalu, bonus APIs ka pehla working version.

| Time | Track | Task | Tool | Output / Deliverable |
| --- | --- | --- | --- | --- |
| 9:00–12:00 | Track A | Preprocessing script generate karo (resize, augmentation, train/val/test split) aur Colab pe ek chhota baseline training run karke pipeline confirm karo. | Antigravity + Gemini, Colab | Working preprocessing script + baseline run log |
| 9:00–12:00 | Track B | Flask/FastAPI app skeleton generate karo with /predict route (abhi dummy output), Postman se test karo. | Antigravity + Gemini, Postman | Running local API (dummy response) |
| 9:00–12:00 | Track C | Upload form + result-display page ka pehla version generate karo, dummy backend se connect karo. | Antigravity + Gemini | UI shows dummy prediction |
| 9:00–12:00 | Track D | Weather-fetch function likho (city/coords se forecast), dummy soil-moisture input ke saath irrigation-decision function jodo. | Antigravity + Gemini, OpenWeatherMap | irrigation_check() function working |
| 9:00–12:00 | Track E | Ek sample farmer question ke upar Gemini/Claude API se grounded response generate karke test karo. | Gemini/Claude API | Sample Q&A working |
| 12:00–13:00 | Track F | requirements.txt aur environment-setup instructions likho, README ka skeleton (headings only) banao. | Claude | README v0 (structure only) |
| 14:00–17:00 | Track A | Full fine-tuning run Colab pe overnight ke liye set karo (checkpointing on), progress monitor karo. | Colab GPU | Training in progress / checkpoint saved |
| 14:00–17:00 | Track B | predict() ka response-structure spec (Section 4.1) ke exact format me match karo — class_label string format finalize. | Antigravity + Gemini | API response format locked |
| 14:00–17:00 | Track C | UI ko farmer-friendly language me style karo — simple words, clear buttons. | Antigravity + Gemini | Styled UI v1 |
| 14:00–17:00 | Track D | Sustainability-score formula draft likho (water-efficiency + resource-use + crop-health ka simple weighted formula), formula document karo. | Claude | Formula written + example calc |
| 14:00–17:00 | Track E | Regional-language (Hindi/Gujarati) output add karo prompt me, dono language me test karo. | Gemini/Claude API | Bilingual response working |
| 17:00–17:30 | Track F | Track B ka skeleton clean machine pe README-instructions follow karke chalane ki koshish karo, gaps note karo. | Manual test | Reproducibility gap-list |
| 18:30–19:00 | All | Evening sync — training progress check, Day 3 target confirm. | — | Day 3 plan locked |

## Day 3 — 12 September — Model Freeze + Real Integration

Goal: Trained model ka evaluation lock karo, backend me real predictions jodo, frontend ko live data se connect karo.

| Time | Track | Task | Tool | Output / Deliverable |
| --- | --- | --- | --- | --- |
| 9:00–11:00 | Track A | Trained model evaluate karo held-out sample pe — macro-F1, confusion matrix, per-class precision/recall calculate karo. | Colab | Evaluation numbers + confusion matrix image |
| 9:00–11:00 | Track B | Dummy /predict ko real model.predict() call se replace karo, 5-10 sample images pe Postman se test karo. | Antigravity + Gemini, Postman | Real predictions returning correctly |
| 9:00–11:00 | Track C | Frontend ko real backend API se connect karo, confidence-score aur precaution-text display karo. | Antigravity + Gemini | End-to-end real prediction visible in UI |
| 9:00–11:00 | Track D | Sustainability-score ko UI-ready format me convert karo (number + 1-line suggestion). | Antigravity + Gemini | Sustainability module output ready |
| 9:00–11:00 | Track E | Assistant ko real prediction result ke saath jodo — asli disease-name par based explanation generate karo. | Gemini/Claude API | Assistant now grounded on real model output |
| 11:00–13:00 | Track F | Model-report (Section 7.3) ke fields fill karna shuru karo — Task, Dataset & split, Model/approach — Track A ke numbers ke saath. | Claude | Model report v0 (partial) |
| 14:00–16:00 | Track A | Agar macro-F1 baseline se kam hai to augmentation/epochs tweak karke dobara train karo, dono results compare karo. | Colab | Final chosen model + comparison note |
| 14:00–16:00 | Track B | Error handling add karo — invalid image, missing file, wrong format ke liye proper error response. | Antigravity + Gemini | Robust API (edge cases handled) |
| 14:00–16:00 | Track C | Loading-state aur error-state UI me add karo (image process ho rahi hai / kuch galat hua). | Antigravity + Gemini | UI states complete |
| 14:00–16:00 | Track D | 3 sample scenarios pe weather+irrigation+sustainability module test karo end-to-end. | Postman, manual test | 3 verified scenario outputs |
| 14:00–16:00 | Track E | Assistant ko English + regional language, dono me test karo; galat/hallucinated jawab mile to prompt tighten karo. | Gemini/Claude API | Stable bilingual grounded assistant |
| 16:00–17:00 | All | Model version freeze karo — jo bhi final weights hai wahi ab se use hoga, dobara retrain sirf critical bug ho to. | — | Frozen model weights (v-final) |
| 18:00–18:30 | All | Evening sync — freeze confirm, Day 4 (integration day) ka plan. | — | Day 4 plan locked |

## Day 4 — 13 September — Full Integration Day

Goal: Saare modules ek hi app me merge, deploy karo, aur end-to-end poora flow test karo.

| Time | Track | Task | Tool | Output / Deliverable |
| --- | --- | --- | --- | --- |
| 9:00–12:00 | Track B | Track D aur Track E ke routes ko main backend app me merge karo — ek unified API structure banao (/predict, /irrigation, /weather, /sustainability, /assistant). | Antigravity + Gemini | Single unified backend |
| 9:00–12:00 | Track C | Saare module-outputs ko ek hi results-screen me integrate karo (disease + irrigation + weather + sustainability + assistant text). | Antigravity + Gemini | Complete single-screen result view |
| 9:00–12:00 | Track A | Track B ko model-integration me support karo (loading path, preprocessing consistency image-input ke liye). | Support role | No integration mismatch |
| 9:00–12:00 | Track D | Sustainability-score display formatting finalize karo, formula README ke liye likh ke rakho. | Claude | Formula documented |
| 9:00–12:00 | Track E | Regional-language toggle ko UI ke saath final jodo (dropdown/button se language switch). | Antigravity + Gemini | Language toggle working in UI |
| 9:00–12:00 | Track F | Streamlit Cloud / Hugging Face Spaces pe deployment setup karo, environment variables (API keys) secure add karo. | Streamlit Cloud / HF Spaces | Live deployment link |
| 14:00–17:00 | All | Full end-to-end test — naya image upload karo, poora flow (disease detection se lekar assistant reply tak) verify karo, kam se kam 5 alag images pe. | Live app, Postman | 5 verified end-to-end runs |
| 17:00–18:00 | Track F | Bugs ka list banao (kaunsa bug kis track se related hai), track-wise assign karo. | Shared doc | Bug list with owners |
| 18:30–19:00 | All | Evening sync — feature-freeze confirm karo (aaj ke baad koi naya feature nahi, sirf bug-fix aur polish). | — | Feature freeze declared |

## Day 5 — 14 September — QA, Documentation & Demo Prep

Goal: Code review, README + model report complete, demo video ka pehla cut ready.

| Time | Track | Task | Tool | Output / Deliverable |
| --- | --- | --- | --- | --- |
| 9:00–11:00 | Track F | Poora codebase Claude ko dikhake full review karwao — bugs, security issues, README ki accuracy cross-check. | Claude (Sonnet) | Review notes + fix-list |
| 9:00–11:00 | Track A | Model report ke saare fields final numbers ke saath complete karo (metric, baseline comparison, limitations). | Claude | Model report — final draft |
| 9:00–11:00 | Track B | Day 4 bug-list se apne track ke bugs fix karo. | Antigravity + Gemini | Backend bugs closed |
| 9:00–11:00 | Track C | UI polish — mobile responsiveness check, accessibility (font-size, contrast) check. | Manual + browser devtools | Polished, responsive UI |
| 9:00–11:00 | Track D & E | Apne-apne bugs fix karo, outputs ki wording ek baar aur farmer-friendly language me check karo. | Antigravity + Gemini | Bonus modules bug-free |
| 11:00–13:00 | Track F | README ke saare 6 required sections likho — modules built, setup/run steps, dataset source, metrics, architecture, limitations, demo-link. | Claude | README — final |
| 14:00–15:00 | All | GitHub repo ko fresh-clone karke README instructions follow karte hue chalao — 10 min ke andar prediction aana chahiye. | Manual test | Reproducibility confirmed <10 min |
| 15:00–17:00 | Track F | Demo-video ka script likho (intro → core task live demo → bonus modules demo → closing), record karo. | Screen recorder | Demo video — first cut (3-5 min) |
| 17:00–18:00 | All | Originality declaration likho — jo third-party code/notebook/dataset use kiya wo README me list karo. | Claude (drafting) | Originality declaration added |
| 18:30–19:00 | All | Evening sync — video review, kal final submission ka plan. | — | Day 6 plan locked |

## Day 6 — 15 September — Final Submission Day

Goal: Sab kuch final commit, video final, repo check aur submission.

| Time | Track | Task | Tool | Output / Deliverable |
| --- | --- | --- | --- | --- |
| 9:00–10:30 | Track F | Demo-video final edit karo, unlisted link generate karo (YouTube/Drive). | Video editor | Final demo video link |
| 9:00–11:00 | All | Section 7.1 ke against repo-structure ek-ek line check karo (README, /src ya /app, /model, /report, requirements.txt). | Checklist (Section below) | Structure fully compliant |
| 11:00–12:00 | Track A/B | Model weights ko GitHub release/link se attach karo agar size limit se bade hai. | GitHub Releases | Weights accessible |
| 12:00–14:00 | All | Buffer time — last-minute fixes, koi bhi chhoti cheez jo miss hui thi. | — | Zero open bugs |
| 14:00–15:00 | Track F | Final commit push karo, commit history check karo (10-15 Sept window ke andar hi real development dikhna chahiye). | GitHub | Clean commit history |
| 15:00–16:00 | All | Final submission — GitHub repo link submit karo deadline se pehle. | Submission portal | Submitted |

# 8. Daily Sync Meeting Format

Har din ek chhoti evening sync (15-20 min) rakho — lamba meeting nahi, sirf status aur blockers.

- Kya complete hua aaj (har track 1 line me bataye).

- Koi blocker hai jo doosre track pe depend karta hai?

- Kal ka top priority kya hai — agar time kam pade to sabse zaroori kaunsa task hai?

- Model/API me koi breaking change hua to sabko turant batao (backend/frontend dono affect hote hain).

# 9. Bonus Module Specification

Teen bonus modules — sabse achha effort-to-impact ratio, hardware ki zaroorat nahi:

| Module | Kaise banega |
| --- | --- |
| Weather-Based Intelligence (C) | OpenWeatherMap se forecast le kar simple rules apply karo: rain-probability high → 'delay irrigation'; temperature-based disease-risk note karo. |
| Smart Irrigation (B) | Soil-moisture (manual/simulated input) + weather forecast combine karke 'irrigate now' / 'wait' decide karo. Logic README me document karo — ye scored gate hai. |
| Farmer Assistant — GenAI (E) | Disease-prediction result + precaution-list ko Gemini/Claude API se plain Hindi/Gujarati explanation me convert karo. Grounded rakhna — free-form advice avoid karo. |

# 10. Testing & QA Checklist

- Har API route Postman se 3+ different inputs pe test kiya.

- Invalid image / missing file / wrong-format ke liye proper error message aata hai.

- predict() ka output format Section 4.1 ke exact contract se match karta hai.

- Fresh clone se README follow karke app 10 min ke andar chal jaata hai.

- UI mobile pe bhi readable aur usable hai.

- Assistant ka regional-language output sahi aur grounded hai (hallucination check kiya).

- Model held-out set pe hi evaluate hua hai, training set pe nahi (leakage check).

# 11. README & Model Report Templates

### README.md — required sections

- Kaunse core + bonus modules banaye.

- Setup aur run instructions (judge 10 min me reproduce kar sake).

- Dataset used aur uska source/licence.

- Har model ke reported metrics (core: macro-F1 + confusion matrix).

- Architecture overview aur known limitations.

- Demo-video link aur deployed-app link.

- Originality declaration — third-party code/notebooks ka credit.

### Model report (one page) — required fields

| Field | Kya likhna hai |
| --- | --- |
| Task | e.g. crop-disease image classification, N classes. |
| Dataset & split | Source, sizes, exact train/validation/test split. |
| Model / approach | Architecture, backbone, key hyperparameters. |
| Metric & result | Macro-F1 (primary) + accuracy, confusion matrix, per-class precision/recall. |
| Baseline | Provided baseline number aur uske saath comparison. |
| Limitations | Honest failure cases — jaise real-field vs lab images. |

# 12. Glossary — Key Terms

| Term | Matlab |
| --- | --- |
| Macro-F1 | Har class ka F1-score alag nikal ke unka simple average — imbalanced classes ke liye raw accuracy se better metric. |
| Confusion matrix | Ek grid jo dikhata hai model kaunsi class ko kis class galat samajh raha hai. |
| Transfer learning | Ek pretrained model (already bade dataset pe trained) ko apne chhote dataset pe fine-tune karna. |
| Held-out test set | Wo data jis pe model kabhi train nahi hua — sirf final evaluation ke liye organizers use karte hain. |
| Grounded response | AI ka jawab sirf diye gaye facts/data par based ho, bahar se kuch invent na kare. |
| Reproducibility | Koi bhi judge README follow karke fresh machine pe app chala sake, without extra manual steps. |

# 13. Risk & Contingency Plan

| Risk | Mitigation |
| --- | --- |
| Macro-F1 baseline se kam aaya | Augmentation badhao, epochs/learning-rate tweak karo, class-imbalance ke liye weighted loss try karo. Track A + Track F dono involve. |
| Training Colab pe slow/disconnect ho raha hai | Checkpointing on rakho, Kaggle Notebooks backup ke roop me use karo. |
| Bonus module time consume kar raha hai | Sirf 3 recommended module tak limit karo, extra module skip karo — core task pe zyada weight hai. |
| README se app nahi chal raha (reproducibility fail) | Fresh machine/venv pe har roz test karo, sirf last-day pe nahi. |
| GenAI assistant free-form/wrong advice de raha hai | Prompt ko strictly grounded rakho — sirf model output + fixed precaution-list par based rakho. |

# 14. Final Pre-Submission Checklist

- /README.md — sab 7 required points cover.

- /src ya /app — source code complete.

- /model — training + predict interface + weights (release/link se agar large).

- /report — one-page model report complete.

- requirements.txt + environment instructions.

- Originality declaration README me.

- Demo video (3-5 min) — core task + bonus modules dikh rahe hain.

- Commit history 10-15 Sept window ke andar hi hai.

- Live deployed-app link working hai.

# 15. Evaluation Criteria & Scoring Strategy

| Parameter | Weight | Team ka focus kya ho |
| --- | --- | --- |
| AI/ML Implementation | 25 | Held-out macro-F1, honest split, no leakage — Track A ka sabse bada focus. |
| Technical Implementation | 20 | Reproducibility — README se chalta hai ya nahi, Track F daily check kare. |
| Innovation & Creativity | 15 | Standard tutorial se aage — regional-language + grounded assistant yahi differentiate karega. |
| Sustainability & Impact | 15 | Quantified benefit chahiye — sustainability-score formula publish karna zaroori. |
| User Experience | 10 | Farmer-friendly clarity, mobile-usability, regional language. |
| Problem Understanding | 10 | Model report me honest limitations likhna. |
| Presentation & Demo | 5 | Video clear aur complete — script pehle se likh ke record karo. |

45 points (AI/ML + Technical) sirf Track A aur Track F ke output pe depend karta hai. Bonus modules acche bhi ho aur incomplete bhi ho jaaye, core-task aur reproducibility kabhi compromise mat karna.

# Appendix A — Shared Class List (example)

Exact final list kickoff-data ke saath ship hogi — ye sirf reference ke liye hai ki class-list kis tarah ki dikhegi (PlantVillage aur PlantDoc dono me common).

| Crop | Classes (disease + healthy) |
| --- | --- |
| Tomato | Early Blight, Late Blight, Leaf Mould, Bacterial Spot, Healthy |
| Potato | Early Blight, Late Blight, Healthy |
| Corn | Common Rust, Grey Leaf Spot, Healthy |
| Apple | Scab, Black Rot, Healthy |
| Grape | Black Rot, Healthy |
| Bell Pepper | Bacterial Spot, Healthy |

Kickoff data aane ke baad ye table exact final list se update kar lena — training se pehle.

# Appendix B — Credentials & Access Tracker

Har API key/login kaun manage kar raha hai aur kahan store hai — shared doc ke private tab me actual keys rakho, yahan sirf status track karo.

| Service | Owner track | Key location (fill in) | Status |
| --- | --- | --- | --- |
| GitHub repo | Track F | — | Created |
| Kaggle account | Track A | — | Pending |
| OpenWeatherMap API key | Track D | — | Pending |
| Gemini API key | Track E | — | Pending |
| Claude API key | Track E / F | — | Pending |
| Streamlit Cloud / HF Spaces login | Track F | — | Pending |

Status column har evening sync me update karo — Pending / In progress / Done.

# Appendix C — Team Working Agreement

Ye chhote norms follow karne se coordination overhead kam ho jaata hai, khaaskar jab 6 log parallel kaam kar rahe ho.

### Git & commits

- Har track apni branch pe kaam kare (e.g. track-a-model, track-b-backend); main branch sirf tested code se update ho.

- Commit messages clear ho — 'Track A: baseline training script added', na ki 'update' ya 'fix'.

- Din me kam se kam 1 commit har active track se — ye commit-history hi originality/timeline proof banti hai.

### Code & prompts

- Antigravity+Gemini se code lene se pehle Claude se spec/prompt clear karo — bina spec ke direct code mangna rework badhata hai.

- Koi bhi API key code me hardcode mat karo — environment variable/.env file use karo (aur .env ko .gitignore me daalo).

- Naya module merge karne se pehle apne track ke andar ek baar self-test kar lo, phir hi main me daalo.

### Communication

- Blocker ho to turant group-chat me daalo — evening sync tak wait mat karo agar koi doosre track ko rok raha hai.

- Bade decision (bonus-module drop/add, model-change) poori team ke sync me hi lena, individually mat karo.

# Appendix D — Backup Plan if a Member is Unavailable

6-log team me agar ek din koi member available na ho, to poora track ruk na jaaye — isliye har track ka ek 'buddy' track pehle se decide kar lo jo basic context jaanta ho.

| Primary track | Backup track | Backup sirf yeh kare |
| --- | --- | --- |
| Track A (Model) | Track F | Training-run monitor karna aur agar crash ho to restart karna — full retraining ka decision nahi lena. |
| Track B (Backend) | Track C | Chhote bug-fix aur restart; naya route add karne ka decision wait kare. |
| Track C (Frontend) | Track B | UI ka chhota fix; naya feature add mat karo. |
| Track D (Weather/Irrigation) | Track E | API-key/connectivity issue fix karna. |
| Track E (Assistant) | Track D | Prompt me chhoti tweak; naya language add mat karo. |
| Track F (Docs/Testing) | All | Har track apne hisse ka README-section khud likh de us din. |

Backup track sirf 'chalu rakhna' ke liye hai — bade architectural decisions primary track ke wapas aane tak rukna chahiye.